## 24 March 2019
Test Case | Remarks | Checked by | Reviewed By
Successful linking of domain name to elastic IP Visit http://www.esmscp.tk/ Ensure that SCP’s front page loads successfully | Landing Page is visible | DL | KK
Successful installation of SSL Certificate Visit https://www.esmscp.tk/ Click on lock icon beside web address Verify that “Connection is secure” is shown in the pop-up | Landing Page has SSL certificate | DL | KK
Successful installation of htop Access SSH terminal Type “htop --version” Verify that command outputs “htop 1.0.1” to confirm that htop is installed | htop is installed | DL | KK
Nginx Server works correctly Access SSH terminal Type “service nginx status” Verify that command outputs “nginx (pid 27083) is running…” to confirm Nginx server has started | Nginx server has started | DL | KK
Correct security group settings Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Security Groups under Network and Security Select group with Group Name of “launch-wizard-1” Click on the inbound tab at the bottom of the screen Visually confirm that security group is correct | Security group has the necessary inbound rules (HTTP Port 80, SSH Port 22, Custom TCP Rule Port 8000 - 8999 & HTTPS Port 443) | DL | KK
Correct Tags Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > EC2 > Running Instance Select on SCP instance > tags > check that the tags are created | Tags for AWS instance, ‘Backup = yes, BackupNoReboot = true, BackupRetentionDays = 1’ has been created for automated AMI backup | DL | KK
Valid SSL Certificate Visit https://www.ssllabs.com/ssltest/ and enter ‘esmscp.tk’ then submit Wait for the test to finish running | The certificate ranking is valid | DL | KK
Successful linking Cloudtopus to AWS instance Visit https:/www.cloudtopus.com and login with SMU Google Account Click on the “Monitor” tab at the front page Verify that Parent Server Status is “Live” Verify that WebApp Status is “Live” | Cloudtopus is able to monitor status of application. | DL | KK
Successful setting of AWS Alarms Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > Cloudwatch under Management & Governance Verify that alarms are set on dashboard | All relevant AWS Alarms have been set and are in operation, by viewing the “Monitoring” panel in the particular instance. | DL | KK
The server can handle 50 concurrent requests Check that siege is installed on lab account’s instance SSH into lab account’s instance Type ‘siege esmscp.tk -c 50’ for 50 users. After 5 to 10 minutes, press Ctrl + C to terminate and see summary. | The server is able to handle the requests with 100% uptime for 50 users. | DL | KK
The application can display the Google Slides without any errors Clicking ‘play’ will take the user to the next slide Users can toggle between slides Users are able to turn on ‘laser pointer’ mode and ‘fullscreen’ mode | Yes | DL | KK
Nagios Server is up and can be accessed Go to http://3.1.98.215/nagios/ Login with nagiosadmin Verify that user can login and see Nagios Homepage | Yes | DL | KK
SCP can monitored and is running Go to Nagios Homepage In the left panel under Current Status, click Services Verify that ClientSCP’s services are up and running (Status is OK and green) | Yes | DL | KK
FreshPing is able to ping all instances | Yes | DL | KK
VisualPing is able to track changes for all instances | Yes | DL | KK

## 17 March 2019
Test Case | Remarks | Checked by | Reviewed By
Successful linking of domain name to elastic IP Visit http://www.esmscp.tk/ Ensure that SCP’s front page loads successfully | Landing Page is visible | DL | KK
Successful installation of SSL Certificate Visit https://www.esmscp.tk/ Click on lock icon beside web address Verify that “Connection is secure” is shown in the pop-up | Landing Page has SSL certificate | DL | KK
Successful installation of htop Access SSH terminal Type “htop --version” Verify that command outputs “htop 1.0.1” to confirm that htop is installed | htop is installed | DL | KK
Nginx Server works correctly Access SSH terminal Type “service nginx status” Verify that command outputs “nginx (pid 27083) is running…” to confirm Nginx server has started | Nginx server has started | DL | KK
Correct security group settings Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Security Groups under Network and Security Select group with Group Name of “launch-wizard-1” Click on the inbound tab at the bottom of the screen Visually confirm that security group is correct | Security group has the necessary inbound rules (HTTP Port 80, SSH Port 22, Custom TCP Rule Port 8000 - 8999 & HTTPS Port 443) | DL | KK
Correct Tags Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > EC2 > Running Instance Select on SCP instance > tags > check that the tags are created | Tags for AWS instance, ‘Backup = yes, BackupNoReboot = true, BackupRetentionDays = 1’ has been created for automated AMI backup | DL | KK
Valid SSL Certificate Visit https://www.ssllabs.com/ssltest/ and enter ‘esmscp.tk’ then submit Wait for the test to finish running | The certificate ranking is valid | DL | KK
Successful linking Cloudtopus to AWS instance Visit https:/www.cloudtopus.com and login with SMU Google Account Click on the “Monitor” tab at the front page Verify that Parent Server Status is “Live” Verify that WebApp Status is “Live” | Cloudtopus is able to monitor status of application. | DL | KK
Successful setting of AWS Alarms Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > Cloudwatch under Management & Governance Verify that alarms are set on dashboard | All relevant AWS Alarms have been set and are in operation, by viewing the “Monitoring” panel in the particular instance. | DL | KK
The server can handle 50 concurrent requests Check that siege is installed on lab account’s instance SSH into lab account’s instance Type ‘siege esmscp.tk -c 50’ for 50 users. After 5 to 10 minutes, press Ctrl + C to terminate and see summary. | The server is able to handle the requests with 100% uptime for 50 users. | DL | KK
The application can display the Google Slides without any errors Clicking ‘play’ will take the user to the next slide Users can toggle between slides Users are able to turn on ‘laser pointer’ mode and ‘fullscreen’ mode | Yes | DL | KK
Nagios Server is up and can be accessed Go to http://3.1.98.215/nagios/ Login with nagiosadmin Verify that user can login and see Nagios Homepage | Yes | DL | KK
SCP can monitored and is running Go to Nagios Homepage In the left panel under Current Status, click Services Verify that ClientSCP’s services are up and running (Status is OK and green) | Yes | DL | KK
FreshPing is able to ping all instances | Yes | DL | KK

## 10 March 2019
Test Case | Remarks | Checked by | Reviewed By
Successful linking of domain name to elastic IP Visit http://www.esmscp.tk/ Ensure that SCP’s front page loads successfully | Landing Page is visible | DL | KK
Successful installation of SSL Certificate Visit https://www.esmscp.tk/ Click on lock icon beside web address Verify that “Connection is secure” is shown in the pop-up | Landing Page has SSL certificate | DL | KK
Successful installation of htop Access SSH terminal Type “htop --version” Verify that command outputs “htop 1.0.1” to confirm that htop is installed | htop is installed | DL | KK
Nginx Server works correctly Access SSH terminal Type “service nginx status” Verify that command outputs “nginx (pid 27083) is running…” to confirm Nginx server has started | Nginx server has started | DL | KK
Correct security group settings Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Security Groups under Network and Security Select group with Group Name of “launch-wizard-1” Click on the inbound tab at the bottom of the screen Visually confirm that security group is correct | Security group has the necessary inbound rules (HTTP Port 80, SSH Port 22, Custom TCP Rule Port 8000 - 8999 & HTTPS Port 443) | DL | KK
Correct Tags Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > EC2 > Running Instance Select on SCP instance > tags > check that the tags are created | Tags for AWS instance, ‘Backup = yes, BackupNoReboot = true, BackupRetentionDays = 1’ has been created for automated AMI backup | DL | KK
Valid SSL Certificate Visit https://www.ssllabs.com/ssltest/ and enter ‘esmscp.tk’ then submit Wait for the test to finish running | The certificate ranking is valid | DL | KK
Successful linking Cloudtopus to AWS instance Visit https:/www.cloudtopus.com and login with SMU Google Account Click on the “Monitor” tab at the front page Verify that Parent Server Status is “Live” Verify that WebApp Status is “Live” | Cloudtopus is able to monitor status of application. | DL | KK
Successful setting of AWS Alarms Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > Cloudwatch under Management & Governance Verify that alarms are set on dashboard | All relevant AWS Alarms have been set and are in operation, by viewing the “Monitoring” panel in the particular instance. | DL | KK
The server can handle 50 concurrent requests Check that siege is installed on lab account’s instance SSH into lab account’s instance Type ‘siege esmscp.tk -c 50’ for 50 users. After 5 to 10 minutes, press Ctrl + C to terminate and see summary. | The server is able to handle the requests with 100% uptime for 50 users. | DL | KK
The application can display the Google Slides without any errors Clicking ‘play’ will take the user to the next slide Users can toggle between slides Users are able to turn on ‘laser pointer’ mode and ‘fullscreen’ mode | Yes | DL | KK
Nagios Server is up and can be accessed Go to http://3.1.98.215/nagios/ Login with nagiosadmin Verify that user can login and see Nagios Homepage | Yes | DL | KK
SCP can monitored and is running Go to Nagios Homepage In the left panel under Current Status, click Services Verify that ClientSCP’s services are up and running (Status is OK and green) | Yes | DL | KK

## 3 March 2019
Test Case | Remarks | Checked by | Reviewed By
Successful linking of domain name to elastic IP Visit http://www.esmscp.tk/ Ensure that SCP’s front page loads successfully | Landing Page is visible | DL | KK
Successful installation of SSL Certificate Visit https://www.esmscp.tk/ Click on lock icon beside web address Verify that “Connection is secure” is shown in the pop-up | Landing Page has SSL certificate | DL | KK
Successful installation of htop Access SSH terminal Type “htop --version” Verify that command outputs “htop 1.0.1” to confirm that htop is installed | htop is installed | DL | KK
Nginx Server works correctly Access SSH terminal Type “service nginx status” Verify that command outputs “nginx (pid 27083) is running…” to confirm Nginx server has started | Nginx server has started | DL | KK
Correct security group settings Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Security Groups under Network and Security Select group with Group Name of “launch-wizard-1” Click on the inbound tab at the bottom of the screen Visually confirm that security group is correct | Security group has the necessary inbound rules (HTTP Port 80, SSH Port 22, Custom TCP Rule Port 8000 - 8999 & HTTPS Port 443) | DL | KK
Correct Tags Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > EC2 > Running Instance Select on SCP instance > tags > check that the tags are created | Tags for AWS instance, ‘Backup = yes, BackupNoReboot = true, BackupRetentionDays = 1’ has been created for automated AMI backup | DL | KK
Valid SSL Certificate Visit https://www.ssllabs.com/ssltest/ and enter ‘esmscp.tk’ then submit Wait for the test to finish running | The certificate ranking is valid | DL | KK
Successful linking Cloudtopus to AWS instance Visit https:/www.cloudtopus.com and login with SMU Google Account Click on the “Monitor” tab at the front page Verify that Parent Server Status is “Live” Verify that WebApp Status is “Live” | Cloudtopus is able to monitor status of application. | DL | KK
Successful setting of AWS Alarms Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > Cloudwatch under Management & Governance Verify that alarms are set on dashboard | All relevant AWS Alarms have been set and are in operation, by viewing the “Monitoring” panel in the particular instance. | DL | KK
The server can handle 50 concurrent requests Check that siege is installed on lab account’s instance SSH into lab account’s instance Type ‘siege esmscp.tk -c 50’ for 50 users. After 5 to 10 minutes, press Ctrl + C to terminate and see summary. | The server is able to handle the requests with 100% uptime for 50 users. | DL | KK
The application can display the Google Slides without any errors Clicking ‘play’ will take the user to the next slide Users can toggle between slides Users are able to turn on ‘laser pointer’ mode and ‘fullscreen’ mode | Yes | DL | KK
Nagios Server is up and can be accessed Go to http://3.1.98.215/nagios/ Login with nagiosadmin Verify that user can login and see Nagios Homepage | Yes | DL | KK
SCP can monitored and is running Go to Nagios Homepage In the left panel under Current Status, click Services Verify that ClientSCP’s services are up and running (Status is OK and green) | Yes | DL | KK

## 24 February 2019
Test Case | Remarks | Checked by | Reviewed By
Successful linking of domain name to elastic IP Visit http://www.esmscp.tk/ Ensure that SCP’s front page loads successfully | Landing Page is visible | DL | KK
Successful installation of SSL Certificate Visit https://www.esmscp.tk/ Click on lock icon beside web address Verify that “Connection is secure” is shown in the pop-up | Landing Page has SSL certificate | DL | KK
Successful installation of htop Access SSH terminal Type “htop --version” Verify that command outputs “htop 1.0.1” to confirm that htop is installed | htop is installed | DL | KK
Nginx Server works correctly Access SSH terminal Type “service nginx status” Verify that command outputs “nginx (pid 27083) is running…” to confirm Nginx server has started | Nginx server has started | DL | KK
Correct security group settings Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Security Groups under Network and Security Select group with Group Name of “launch-wizard-1” Click on the inbound tab at the bottom of the screen Visually confirm that security group is correct | Security group has the necessary inbound rules (HTTP Port 80, SSH Port 22, Custom TCP Rule Port 8000 - 8999 & HTTPS Port 443) | DL | KK
Correct Tags Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > EC2 > Running Instance Select on SCP instance > tags > check that the tags are created | Tags for AWS instance, ‘Backup = yes, BackupNoReboot = true, BackupRetentionDays = 1’ has been created for automated AMI backup | DL | KK
Valid SSL Certificate Visit https://www.ssllabs.com/ssltest/ and enter ‘esmscp.tk’ then submit Wait for the test to finish running | The certificate ranking is valid | DL | KK
Successful linking Cloudtopus to AWS instance Visit https:/www.cloudtopus.com and login with SMU Google Account Click on the “Monitor” tab at the front page Verify that Parent Server Status is “Live” Verify that WebApp Status is “Live” | Cloudtopus is able to monitor status of application. | DL | KK
Successful setting of AWS Alarms Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > Cloudwatch under Management & Governance Verify that alarms are set on dashboard | All relevant AWS Alarms have been set and are in operation, by viewing the “Monitoring” panel in the particular instance. | DL | KK
The server can handle 50 concurrent requests Check that siege is installed on lab account’s instance SSH into lab account’s instance Type ‘siege esmscp.tk -c 50’ for 50 users. After 5 to 10 minutes, press Ctrl + C to terminate and see summary. | The server is able to handle the requests with 100% uptime for 50 users. | DL | KK
The application can display the Google Slides without any errors Clicking ‘play’ will take the user to the next slide Users can toggle between slides Users are able to turn on ‘laser pointer’ mode and ‘fullscreen’ mode | Yes | DL | KK

## 17 February 2019
Test Case | Remarks | Checked by | Reviewed By
Successful linking of domain name to elastic IP Visit http://www.esmscp.tk/ Ensure that SCP’s front page loads successfully | Landing Page is visible | DL | KK
Successful installation of SSL Certificate Visit https://www.esmscp.tk/ Click on lock icon beside web address Verify that “Connection is secure” is shown in the pop-up | Landing Page has SSL certificate | DL | KK
Successful installation of htop Access SSH terminal Type “htop --version” Verify that command outputs “htop 1.0.1” to confirm that htop is installed | htop is installed | DL | KK
Nginx Server works correctly Access SSH terminal Type “service nginx status” Verify that command outputs “nginx (pid 27083) is running…” to confirm Nginx server has started | Nginx server has started | DL | KK
Correct security group settings Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Security Groups under Network and Security Select group with Group Name of “launch-wizard-1” Click on the inbound tab at the bottom of the screen Visually confirm that security group is correct | Security group has the necessary inbound rules (HTTP Port 80, SSH Port 22, Custom TCP Rule Port 8000 - 8999 & HTTPS Port 443) | DL | KK
Correct Tags Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > EC2 > Running Instance Select on SCP instance > tags > check that the tags are created | Tags for AWS instance, ‘Backup = yes, BackupNoReboot = true, BackupRetentionDays = 1’ has been created for automated AMI backup | DL | KK
Valid SSL Certificate Visit https://www.ssllabs.com/ssltest/ and enter ‘esmscp.tk’ then submit Wait for the test to finish running | The certificate ranking is valid | DL | KK
Successful linking Cloudtopus to AWS instance Visit https:/www.cloudtopus.com and login with SMU Google Account Click on the “Monitor” tab at the front page Verify that Parent Server Status is “Live” Verify that WebApp Status is “Live” | Cloudtopus is able to monitor status of application. | DL | KK
Successful setting of AWS Alarms Visit AWS and login to project account “mark.tan.2017@smu.edu.sg” Click on Services > Cloudwatch under Management & Governance Verify that alarms are set on dashboard | All relevant AWS Alarms have been set and are in operation, by viewing the “Monitoring” panel in the particular instance. | DL | KK
The server can handle 50 concurrent requests Check that siege is installed on lab account’s instance SSH into lab account’s instance Type ‘siege esmscp.tk -c 50’ for 50 users. After 5 to 10 minutes, press Ctrl + C to terminate and see summary. | The server is able to handle the requests with 100% uptime for 50 users. | DL | KK
The application can display the Google Slides without any errors Clicking ‘play’ will take the user to the next slide Users can toggle between slides Users are able to turn on ‘laser pointer’ mode and ‘fullscreen’ mode | Yes | DL | KK