## SCP Build 1.0.0
Day | Task No. | Task | Planned Start Time | Planned End Time | Actual Start Time | Actual End Time | Team | Responsible | Comments and Notes of Changes | Sign-off | Reviewed by
2019-01-28 | T1 | Retrieve AWS Account ID | 2230 | 2245 | - | - | Server | MT | - | MT | KK
2019-01-28 | T2 | Submission of AWS Account ID to Product Manager | 2300 | 2340 | - | - | Server | MT | - | MT | KK
2019-01-28 | T3 | Register AWS into Cloudtopus environment | 1300 | 1345 | - | - | Server | MT | Successfully registered AWS Account no. 342685487885 | MT | KK
2019-01-28 | T4 | Update Product Manager and obtain production image | 1345 | 1400 | - | - | Server | KK | - | KK | DL
2019-02-07 | T5 | Create Amazon EC2 instance and configure Amazon Machine Instance (AMI), instance type, details, storage, tags, security group | 1215 | 1225 | 1215 | 1227 | Server | JR | Settings are configured based on Lab1. Tag Name changed to IS214-G5T7-Project | JR | DL
2019-02-07 | T6 | Download Key Pair (.PEM file) and launch AWS instance | 1225 | 1227 | 1233 | 1237 | Server | JR | .PEM file downloaded and instance Launched | JR | DL
2019-02-07 | T7 | Create 'Access Key ID' and 'Secret Access Key' from security credential settings and download them | 1227 | 1232 | 1237 | 1240 | Server | MT | Security credentials are downloaded as root.csv | MT | DL
2019-02-07 | T8 | Convert .PEM file into .PPK format using PuTTYgen | 1232 | 1235 | 1240 | 1242 | Server | MT | Converted and saved as private key | MT | DL
2019-02-07 | T9 | Configure connection information using standalone SSH Client PuTTy and connect to AWS instance | 1235 | 1240 | 1242 | 1244 | Server | MT | - | MT | DL
2019-02-07 | T10 | Configure and authenticate connection to AWS in SSH terminal | 1240 | 1245 | 1244 | 1250 | Server | MT | Authentication successful | MT | DL
2019-02-07 | T11 | Create new Elastic IP address and assign AWS instance | 1245 | 1255 | 1250 | 1253 | Server | MT | Successfully associated Elastic IP address | MT | KK
2019-02-07 | T12 | Restart (Stop and Start) AWS instance, and test the deployment with the new Elastic IP address | 1255 | 1300 | 1253 | 1256 | Server | MT | Successful Link: http://3.1.118.42:8000/ | MT | KK
2019-02-07 | T13 | Upgrade security packages and frameworks for security | 1330 | 1400 | 1333 | 1357 | Security | DL | - | DL | JR
2019-02-07 | T14 | Upload SSL Certificate to web server | 1430 | 1440 | 1419 | 1429 | Security | DL | - | DL | JR
2019-02-07 | T15 | Configure Nginx HTTPS server | 1440 | 1500 | 1429 | 1435 | Security | DL | - | DL | JR
2019-02-07 | T16 | Configure reverse proxy for root path | 1500 | 1520 | 1435 | 1452 | Security | DL | - | DL | JR
2019-02-07 | T17 | Manual Monitoring using terminal | 1200 | 1230 | 2045 | 2105 | Security | JL | - | JL | KK
2019-02-07 | T18 | Check status of Automated Monitoring using alarms | 1230 | 1240 | 2105 | 2120 | Security | JL | Ensured that Alarm for Status Check Fail is running | JL | KK
2019-02-07 | T19 | Monitoring using Control Charts(AWS Cloudwatch) | 1240 | 1310 | 2120 | 2130 | Security | JL | - | JL | KK
2019-02-07 | T20 | Monitoring using Cloudtopus | 1310 | 1325 | 2130 | 2140 | Security | JL | - | JL | KK
2019-02-07 | T21 | Implementation Test | 1400 | 1430 | 2200 | 2215 | Security | DL | - | DL | KK
2019-02-08 | T22 | Backup AMI before additional configurations | 2200 | 2215 | 2200 | 2207 | Security | DL | AMI has been successfully created | DL | KK
2019-02-13 | T23 | Install SSL certificate on nginx | 2100 | 2200 | 2100 | 2153 | Server | JR | 1) Certificate is valid 2) Redirection to https://www.esmscp.tk successful | JR | DL
2019-02-17 | T24 | Load Balancing on ec2 instance | 1600 | 1730 | 1600 | 1715 | Server | JR | Transactions: 271392 hits Availability: 100% Elapsed time: 481.85 secs Data transferred: 83.86 MB Response time: 0.02 secs Transaction rate: 563.21 trans/sec Throughput: 0.17 MB/sec Concurrency: 9.40 Successful transactions: 271392 Failed transactions: 0 Longest transaction: 1.15 Shortest transaction: 0.00 | JR | DL
2019-02-17 | T25 | Extra steps to harden nginx server | 2230 | 2300 | 2210 | 2240 | Security | JR | - | JR | DL
2019-02-17 | T26 | Implementation Test | 2300 | 2345 | 2245 | 2330 | Security | DL | Ensure all systems are working as intended | DL | KK
2019-02-18 | T27 | Backup AMI before additional configurations | 1900 | 1915 | 1900 | 1907 | Security | DL | AMI has been successfully created | DL | KK
2019-02-18 | T28 | Automatic Backup of AMI | 1915 | 1945 | 1907 | 1932 | Security | DL | Snapshot of AMI has been successfully created | DL | KK
2019-02-18 | T29 | Implementation Test | 1945 | 2030 | 1932 | 2015 | Security | DL | Ensure all systems are working as intended | DL | KK

## 17 February 2019
Day | Task No. | Task | Planned Start Time | Planned End Time | Actual Start Time | Actual End Time | Team | Responsible | Comments and Notes of Changes | Sign-off | Reviewed by