## SCP Build 1.0.0
|  |  |  | Date of deployment | 2019-02-18
|  |  |  | Change number | SCP Build 1.0.0
|  |  |  | Business Owner | Rafael J. Barros
|  |  |  | Deployment owner | Kenny Kwek
Day | Start Time | End Time | Task No. | Task | Team | Responsible | Preparation | Post-check | Dependency | Status
2019-01-28 | 2230 | 2245 | T1 | Retrieve AWS Account ID | Server | MT | Creation and verification of Amazon Web Services (AWS) Account | Ensure account can be logged in successfully | - | Completed
2019-01-28 | 2300 | 2340 | T2 | Submission of AWS Account ID to Product Manager | Server | MT | Obtain AWS Account ID | Ensure approval by QA | T1 | Completed
2019-01-28 | 1300 | 1345 | T3 | Register AWS into Cloudtopus environment | Server | MT | Approval from Product Manager | Receive success message for registration of account | T2 | Completed
2019-01-28 | 1345 | 1400 | T4 | Update Product Manager and obtain production image | Server | KK | Submit deployment plan to e-learn and email Product Manager for approval | Check if image can be accessed | T3 | Completed
2019-02-07 | 1215 | 1225 | T5 | Create Amazon EC2 instance and configure Amazon Machine Instance (AMI), instance type, details, storage, tags, security group | Server | MT | Prepare released deployment image by release team | Configured AWS instance environment with correct settings and details | T4 | Completed
2019-02-07 | 1225 | 1227 | T6 | Download Key Pair (.PEM file) and launch AWS instance | Server | MT | Configured AWS instance environment with correct settings and details | .PEM File downloaded and AWS instance successfully launched | T5 | Completed
2019-02-07 | 1227 | 1232 | T7 | Create 'Access Key ID' and 'Secret Access Key' from security credential settings and download them | Server | MT | .PEM File downloaded and AWS instance successfully launched | Key file containing 'Access Key ID' and 'Secret Key Access' | T6 | Completed
2019-02-07 | 1232 | 1235 | T8 | Convert .PEM file into .PPK format using PuTTYgen | Server | MT | Prepare .PEM File | .PPK File Downloaded | T7 | Completed
2019-02-07 | 1235 | 1240 | T9 | Configure connection information using standalone SSH Client PuTTy and connect to AWS instance | Server | MT | Information needed to connect: 1) Public AWS DNS(IP Address) from AWS console 2) Auto-login username: 'ec2-user' 3) Authentication: imported .PPK file | Connection successful with SSH terminal opened | T8 | Completed
2019-02-07 | 1240 | 1245 | T10 | Configure and authenticate connection to AWS in SSH terminal | Server | MT | 1) Information for 'Access Key ID' and 'Secret Key Access' from Key File 2) Default region 'ap-southeast-1' and output format 'json' | Configuration information successfully entered and SSH terminal exited | T9 | Completed
2019-02-07 | 1245 | 1255 | T11 | Create new Elastic IP address and assign AWS instance | Server | MT | AWS instance successfully launched | Visual validation of successful creation of Elastic IP address and association to instance | T10 | Completed
2019-02-07 | 1255 | 1300 | T12 | Restart (Stop and Start) AWS instance, and test the deployment with the new Elastic IP address | Server | MT | Successful creation and association of instance to new Elastic IP address | Access AWS instance with new Elastic IP address via <elastic ip>:8000 and validate that image is seen on web page | T11 | Completed
2019-02-07 | 1330 | 1400 | T13 | Upgrade security packages and frameworks for security | Security | DL | AWS Instance has been created and is accessible | 1) Patch updated successfully 2) Python Django framework has been updated to the latest release | T12 | Completed
2019-02-07 | 1430 | 1440 | T14 | Upload SSL Certificate to web server | Security | DL | 1) Ensure that SSL Certificate is generated and ready 2) Create directories for certificates and copy them into their corresponding directories | Use ”ls” command to make sure certificate files are available on server | T13 | Completed
2019-02-07 | 1440 | 1500 | T15 | Configure Nginx HTTPS server | Security | DL | 1) Backup nginx file to rollback on 2) Check which security group is in-use | Test syntax correctly entered and load new configurations Verify Nginx is working properly | T14 | Completed
2019-02-07 | 1500 | 1520 | T16 | Configure reverse proxy for root path | Security | DL | Backup nginx config file to rollback on | Test and verify configuration is working | T15 | Completed
2019-02-07 | 2045 | 2105 | T17 | Manual Monitoring using terminal | Security | JL | Installation of htop | Ensure status is being reflected correctly on the feed. | T12 | Completed
2019-02-07 | 2105 | 2120 | T18 | Check status of Automated Monitoring using alarms | Security | JL | Set up Automated alarm in AWS CloudWatch | Ensure notification alert is working | T17 | Completed
2019-02-07 | 2120 | 2130 | T19 | Monitoring using Control Charts(AWS Cloudwatch) | Security | JL | - | Ensure status is being reflected correctly on the feed. | T18 | Completed
2019-02-07 | 2130 | 2140 | T20 | Monitoring using Cloudtopus | Security | JL | - | Ensure status is being reflected correctly on the feed. | T19 | Completed
2019-02-07 | 2200 | 2215 | T21 | Implementation Test | Security | DL | - | Ensure all systems are working as intended | T17,T20 | Completed
2019-02-08 | 2200 | 2215 | T22 | Backup AMI before additional configurations | Security | DL | Ensure that AWS instance environment is working | AMI has been successfully created | T21 | Completed
2019-02-13 | 2100 | 2200 | T23 | Install SSL certificate on nginx | Server | JR | 1) Prepare Domain Name: www.esmscp.tk and esmscp.tk 2) Install required dependencies on nginx | 1) Ensure certificate is valid 2) Ensure redirection to https://www.esmscp.tk | T22 | Completed
2019-02-17 | 1400 | 1430 | T24 | Load Balancing on ec2 instance | Server | JR | 1) Ensure Nginx is running correctly 2) Ensure Siege is installed on lab's Nginx server 3) Gunicorn installed | Availability 100% for 50 users | T23 | Completed
2019-02-17 | 2230 | 2300 | T25 | Extra steps to harden nginx server | Server | JR | Backup nginx config file to rollback on | Test and verify configuration is working | T24 | Completed
2019-02-17 | 2300 | 2345 | T26 | Implementation Test | Security | DL | - | Ensure all systems are working as intended | T25 | Completed
2019-02-18 | 1900 | 1915 | T27 | Backup AMI before additional configurations | Security | DL | Ensure that AWS instance environment is working | AMI has been successfully created | T26 | Completed
2019-02-18 | 1915 | 1945 | T28 | Automatic Backup of AMI | Security | DL | 1) Prepare create AMI script 2) Prepare delete AMI script 3) Prepare roles script 4) Create create and delete AMI function 5) Create IAM role | Snapshot of AMI has been successfully created | T27 | Completed
2019-02-18 | 1945 | 2030 | T29 | Implementation Test | Security | DL | - | Ensure all systems are working as intended | T28 | Completed

## Contacts
Initials | Name | Phone | Email | Manager | Team | Role
KK | Kenny Kwek | 9620 1737 | kenny.kwek.2017@sis.smu.edu.sg | Wendy Tan | Server | Support Manager
DL | Ong De Lin | 8168 9456 | delin.ong.2017@sis.smu.edu.sg | Kenny Kwek | Security | Quality Assurance
JL | Lee Jia Ern, Janell | 8285 7148 | janell.lee.2017@sis.smu.edu.sg | Kenny Kwek | Security | Tier 1 - Communication
MT | Tan Rong Jian Mark | 8405 7248 | mark.tan.2017@sis.smu.edu.sg | Kenny Kwek | Server | Tier 2 - Business Analyst
|  |  |  | Kenny Kwek | Server | Tier 3 - Dev and Infrastructure
JR | Lau Jun Rong | 9297 1479 | junrong.lau.2017@sis.smu.edu.sg |  |  | Security