## SCP Build 1.0.0
Type | Description | Date | Performed
Monitoring | Cloudtopus registered with AWS account ID | 2019-01-28 | Yes
Approval | Gotten written approval in email from Product Manager (Wendy) | 2019-02-02 | Yes
Team | Deployment team understand their roles and are ready to execute plan | 2019-02-07 | Yes
Plan | Hour-By-Hour Plan (SCP Build 1.0.0) ready | 2019-02-07 | Yes
Software | AWS cloud image from Release Manager (Prof Rafael) | 2019-02-02 | Yes
Software | SCP Build 1.0.0 working | 2019-02-07 | Yes
Network Configuration | 1) Domain name 2) Gunicorn installed | 2019-02-12 | Yes
Security Configuration | SSL Certificate | 2019-02-12 | Yes
Approval | Gotten written approval in email from Product Manager (Wendy) | 2019-02-02 | Yes
Team | Deployment team understand their roles and are ready to execute plan | 2019-02-08 | Yes
Plan | Hour-By-Hour Plan for deploying on 17 February 2019 ready | 2019-02-07 | Yes