## SCP Build 1.0.0
Day | Task No. | Task | Planned Start Time | Planned End Time | Actual Start Time | Actual End Time | Team | Responsible | Notes of Changes | User Sign-off | Final Sign-off
2019-01-28 | T1 | Retrieve AWS Account ID | 2230 | 2245 | - | - | Server | MT
2019-01-28 | T2 | Submission of AWS Account ID to Product Manager | 2300 | 2340 | - | - | Server | MT
2019-01-28 | T3 | Register AWS into Cloudtopus environment | 1300 | 1345 | - | - | Server | MT | Successfully registered AWS Account no. 342685487885
2019-01-28 | T4 | Update Product Manager and obtain production image | 1345 | 1400 | - | - | Server | KK
2019-02-07 | T5 | Create Amazon EC2 instance and configure Amazon Machine Instance (AMI), instance type, details, storage, tags, security group | 1215 | 1225 | 1215 | 1227 | Server | JR | Settings are configured based on Lab1. Tag Name changed to IS214-G5T7-Project
2019-02-07 | T6 | Download Key Pair (.PEM file) and launch AWS instance | 1225 | 1227 | 1233 | 1237 | Server | JR | Instance Launched
2019-02-07 | T7 | Create 'Access Key ID' and 'Secret Access Key' from security credential settings and download them | 1227 | 1232 | 1237 | 1240 | Server | MT | Security credentials are downloaded as root.csv
2019-02-07 | T8 | Convert .PEM file into .PPK format using PuTTYgen | 1232 | 1235 | 1240 | 1242 | Server | MT | Converted and saved as private key
2019-02-07 | T9 | Configure connection information using standalone SSH Client PuTTy and connect to AWS instance | 1235 | 1240 | 1242 | 1244 | Server | MT
2019-02-07 | T10 | Configure and authenticate connection to AWS in SSH terminal | 1240 | 1245 | 1244 | 1250 | Server | MT
2019-02-07 | T11 | Create new Elastic IP address and assign AWS instance | 1245 | 1255 | 1250 | 1253 | Server | MT | Successfully associated Elastic IP address
2019-02-07 | T12 | Restart (Stop and Start) AWS instance, and test the deployment with the new Elastic IP address | 1255 | 1300 | 1253 | 1256 | Server | MT | Successful Link: http://3.1.118.42:8000/
2019-02-07 | T13 | Upgrade security packages and frameworks for security | 1330 | 1400 | 1333 | 1357 | Security | DL
2019-02-07 | T14 | Upload SSL Certificate to web server | 1430 | 1440 | 1419 | 1429 | Security | DL
2019-02-07 | T15 | Configure Nginx HTTPS server | 1440 | 1500 | 1429 | 1435 | Security | DL
2019-02-07 | T16 | Configure reverse proxy for root path | 1500 | 1520 | 1435 | 1452 | Security | DL
2019-02-07 | T17 | Manual Monitoring using terminal | 1200 | 1230 | 2045 | 2105 | Security | JL
2019-02-07 | T18 | Check status of Automated Monitoring using alarms | 1230 | 1240 | 2105 | 2120 | Security | JL | Ensured that Alarm for Status Check Fail is running
2019-02-07 | T19 | Monitoring using Control Charts(AWS Cloudwatch) | 1240 | 1310 | 2120 | 2130 | Security | JL
2019-02-07 | T20 | Monitoring using Cloudtopus | 1310 | 1325 | 2130 | 2140 | Security | JL
2019-02-07 | T21 | Implementation Test | 1400 | 1430 | 2200 | 2215 | Security | DL